## Jira (5)
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Priority | Status | Sprint | Custom field (Story point estimate)
Story | GMFL-45 | 10620 | Finalize AI-driven personalized workout routines |  |  | Highest | Done | GMFL Sprint 3
Story | GMFL-81 | 10915 | App Documentation |  |  | Highest | Done | GMFL Sprint 3
Story | GMFL-47 | 10622 | User testing and feedback-driven improvements |  |  | Highest | In Progress | GMFL Sprint 3
Story | GMFL-88 | 10922 | Accessibility and Inclusion Features |  |  | Highest | In Progress | GMFL Sprint 3
Task | GMFL-76 | 10846 | documentation/scripts on how to run/deploy the application (required api keys, Oauth server workflow) | Raheem Crayton | 630ec429316bbc56c424463c | Highest | Done | GMFL Sprint 3 | 7
Task | GMFL-77 | 10879 | user guide for the sponsor that includes images on how to use functionality | Luke McArthur | 712020:9da60a5d-cd9f-4cb5-8063-ec32550401a6 | Highest | Done | GMFL Sprint 3 | 7
Task | GMFL-79 | 10881 | Test plan with test cases and testing script | Brandon Nguyen | 63c8573cd579d7c6875510ee | Highest | Done | GMFL Sprint 3 | 7
Task | GMFL-83 | 10917 | Backend testing suite (pytest) | Brandon Nguyen | 63c8573cd579d7c6875510ee | High | Done | GMFL Sprint 3 | 7
Task | GMFL-82 | 10916 | Frontend testing suite (jest) | Brandon Nguyen | 63c8573cd579d7c6875510ee | High | Done | GMFL Sprint 3 | 7
Task | GMFL-90 | 10924 | Implement a quick workout section on the home page | Luke McArthur | 712020:9da60a5d-cd9f-4cb5-8063-ec32550401a6 | Medium | Done | GMFL Sprint 3 | 3
Task | GMFL-78 | 10880 | documentation on how to set up the development environment (including dependencies) | Everett Potter | 63065529d25d0a5dd2bdbaa1 | Highest | Done | GMFL Sprint 3 | 7
Task | GMFL-87 | 10921 | Use the LLM to generate user workouts based off of their input | Raheem Crayton | 630ec429316bbc56c424463c | Medium | Done | GMFL Sprint 3 | 4
Task | GMFL-86 | 10920 | Allow users to customize their workout plans | Everett Potter | 63065529d25d0a5dd2bdbaa1 | High | Done | GMFL Sprint 3 | 5
Task | GMFL-91 | 10925 | Add rate limiters to backend routes | Brandon Nguyen | 63c8573cd579d7c6875510ee | Medium | Done | GMFL Sprint 3 | 2
Task | GMFL-85 | 10919 | Setup Wger to expand workout dataset | Raheem Crayton | 630ec429316bbc56c424463c | High | Done | GMFL Sprint 3 | 2
Task | GMFL-84 | 10918 | Setup TestFlight for beta testing | Raheem Crayton | 630ec429316bbc56c424463c | Medium | In Progress | GMFL Sprint 3 | 3
Task | GMFL-89 | 10923 | Implement a screen reader to userflows | Brandon Nguyen | 63c8573cd579d7c6875510ee | High | In Progress | GMFL Sprint 3 | 5
Task | GMFL-71 | 10777 | Setup built-in health app hook for android | Everett Potter | 63065529d25d0a5dd2bdbaa1 | Medium | Done | GMFL Sprint 3 | 5